Key Dates and Milestones

Introduction of Cost Recovery to the National Gene Technology Scheme

| Date | Milestone |
| --- | --- |
| September 2026 | Establishment of Industry Reference Group (IRG) with regulated stakeholders. |
| 6 October 2026 | Cost Recovery Implementation Statement (CRIS) information seminar with industry peak bodies ahead of public consultation. |
| 7 October 2026 – 13 November 2026 | Draft CRIS released for public consultation on OGTR website, alongside cost recovery implementation timeframes. |
| 15 October 2026 | Cost recovery information session at National Institutional Biosafety Committee (IBC) Forum. |
| Late October 2026 | Inaugural Cost Recovery Industry Reference Group (IRG) meeting. Initial meeting will be focused on CRIS and related feedback. |
| Late October 2026 | Information webinar during draft CRIS consultation to address stakeholder questions and concerns. |
| December 2026/January 2027 | Information webinar outlining how stakeholder feedback on the draft CRIS has informed the final CRIS. Progression of final CRIS and related Phase 1 cost recovery arrangements for Ministerial endorsement |
| February 2027 | Related legislative instruments considered at Executive Council Meeting. |
| 1 March 2027 | Phase 1 Cost Recovery arrangements commence. |